# RESOLVE PM — EXECUTION ENGINE EXTRACTION & BUSINESS LOGIC DOCUMENTATION AUDIT

Report Date: May 29, 2026
 Scope: Complete Business Logic Reverse-Engineering
 Audience: Founders, Project Managers, Operations Managers, Business Stakeholders

## SECTION 1: PROJECT LIFECYCLE

### What It Does

A project in Resolve PM is a container that holds all the work (tasks) needed to deliver something — a product launch, a client deployment, an internal initiative. Every project belongs to a single workspace (your company's environment).

### The Status Flow

A project moves through these stages:

Planning → Active → In-Progress → Review → Done → Archived/Deployed

- Planning: The project has been created but work has not formally begun. Tasks may be drafted.

- Active: The project is approved and open for execution. Team members are assigned.

- In-Progress: Work is actively happening. Tasks are being moved through the board.

- Review: All core work is believed complete and the project is under final validation.

- Done: The project is fully delivered. All tasks are resolved.

- Archived: The project is shelved for historical reference. No further changes.

- Deployed: The project has been released to production/clients.

### Required Inputs to Create a Project

- Name: What the project is called (e.g., "Client ERP Deployment")

- Priority: Low, Medium, High, or Urgent

- Execution Mode: How work will be organized — Kanban (continuous flow), Scrum (sprint cycles), SDLC (phase gates), Hybrid, or Custom

- Template: A starting workflow pattern (e.g., "Agile Scrum", "Enterprise Delivery", "Campaign Pipeline", "Site Execution")

- Team Assignment (optional): Which team owns this project

- Client Deadline (optional): The contractual delivery date promised to the client

- Proposed Start Date (optional)

### Ownership Rules

- Every project belongs to a workspace (your company's environment)

- A project can be assigned to a specific team

- A project has an owner (the person who created or leads it)

- Only PMs and Super Admins can create projects

- Developers can view projects they are assigned to, but cannot create them

### Completion Rules

The platform does not have an automated "project complete" trigger. A PM or Super Admin manually changes the project status to "done" or "deployed." There is no system-enforced gate that checks whether all tasks are actually finished before a project is marked complete.

### Example: Complete Project Journey

Scenario: "Mobile App Redesign"

- The PM creates the project with priority "High", template "Agile Scrum", and a client deadline of July 15.

- Status begins at "planning". Tasks are drafted — "UI Wireframes", "API Refactor", "QA Testing".

- The PM changes the status to "active" once sprint planning is done.

- As developers start work, the status moves to "in-progress".

- When the last task enters code review, the PM sets the project to "review".

- After final QA, the PM marks the project "done".

- After deployment to production, they may change it to "deployed" or "archived".

## SECTION 2: TASK LIFECYCLE

### What It Does

A task is a single unit of work inside a project. It represents something one person (or a small group) needs to deliver — for example, "Design the login page" or "Fix the payment API timeout."

### The Status Flow (Execution States)

Backlog → Ready → In Progress → Review → Done

- Backlog: The task exists but is not yet prioritized for immediate work. It's in the queue.

- Ready: The task is prepared and cleared for someone to start working on it.

- In Progress: A developer or team member is actively working on this task.

- Review: The work is done and awaiting validation (code review, QA, client sign-off).

- Done: The task is fully completed and accepted.

### Granular Execution Sub-States

Behind the simple 5-state board, the system tracks much more nuanced states:

Active sub-states: EXECUTING, DEPLOYING, TESTING, VALIDATING
 Waiting sub-states: WAITING_FOR_CLIENT, WAITING_FOR_DATA, WAITING_FOR_INFRASTRUCTURE, WAITING_FOR_APPROVAL
 Blocked sub-states: BLOCKED_DEPENDENCY, BLOCKED_INFRASTRUCTURE, BLOCKED_ACCESS
 Coordination sub-states: CLIENT_VERIFICATION, RELEASE_WINDOW_PENDING, INTERNAL_REVIEW

These map back to the 5 board columns for the visible user interface, but the engine uses them to calculate precise wait times, blocked periods, and execution windows.

### Assignment Rules

- Tasks can be assigned to any user in the workspace

- Developers cannot reassign tasks. Only PMs and Super Admins can change who a task is assigned to. This is enforced at the database level — a developer literally cannot override it.

- Developers cannot move tasks between projects

- Developers cannot change task priority, risk, confidence, predicted completion, or delay drift values

### Who Can Do What

| Action | Developer | PM | Super Admin |
| --- | --- | --- | --- |
| Create tasks | ❌ | ✅ | ✅ |
| Change task status | ✅ | ✅ | ✅ |
| Reassign tasks | ❌ | ✅ | ✅ |
| Change priority | ❌ | ✅ | ✅ |
| Modify estimated hours | ✅ | ✅ | ✅ |
| Modify risk/confidence | ❌ | ✅ | ✅ |
| Move between projects | ❌ | ✅ | ✅ |
| Delete tasks | ❌ | ✅ | ✅ |

### Required Inputs to Create a Task

- Name: What the work is (e.g., "Implement OAuth2 Login")

- Estimated Hours: How long the work is expected to take

- Priority: Low, Medium, High, or Urgent

- PERT Estimates (optional): Best-case, Most-likely, and Worst-case hours

- Assignee (optional): Who will do the work

- Start Date (optional)

- Deadline (optional)

- Dependencies (optional): Which other tasks must finish first

### Example: Complete Task Journey

- PM creates "Build Payment Gateway" — 40 estimated hours, priority High, assigned to Developer A.

- Task starts in Backlog.

- During sprint planning, PM moves it to Ready.

- Developer A begins work → status becomes In Progress.

- Developer A finishes coding → moves to Review.

- QA validates → PM moves to Done.

If during step 4, Developer A hits a server issue, a blocker is logged as "BLOCKED_INFRASTRUCTURE" internally. The task visually stays on the board in "Ready" (waiting) until the blocker is resolved, then returns to "In Progress."

## SECTION 3: TIME & SCHEDULING LOGIC

### The Core Calculation: PERT (Program Evaluation and Review Technique)

This is the mathematical heart of Resolve PM. When someone creates a task, they can provide three time estimates:

- Best case: If everything goes perfectly

- Most likely: The realistic estimate

- Worst case: If everything goes wrong

The formula:
 Expected Effort = (Best + 4 × Most Likely + Worst) ÷ 6

Example: A task with best = 8h, likely = 16h, worst = 32h:
 Expected = (8 + 64 + 32) / 6 = 17.3 hours

The "uncertainty" (standard deviation) is calculated as:
 Uncertainty = (Worst − Best) ÷ 6 = (32 − 8) / 6 = 4 hours

If only "estimated hours" is provided (no PERT), the system uses that single number directly.

### The Adjusted Effort Calculation

The raw PERT estimate is then adjusted by real-world factors:

Adjusted Hours = (Estimated + Interruptions + Uncertainty) × Team Load ÷ (Attendance × Availability × Resource Multiplier)

Where:

- Attendance Factor: How consistently the person actually shows up (1.0 = always, 0.5 = half the time)

- Availability Factor: How much of their day is available (reduced by meetings, leaves)

- Team Load Factor: How overloaded the team is (1.0 = normal, 1.5 = 50% overloaded)

- Interruption Hours: Expected unplanned disruptions

- Resource Multiplier: Based on engineer skill profiles (seniors boost, juniors reduce)

### How Predicted Completion Date Is Calculated

The system takes the adjusted hours and walks forward through the calendar, skipping:

- Non-working days (weekends, Sundays)

- Public holidays (auto-imported based on country)

- Company shutdowns (e.g., Christmas week closure)

- Personal leaves (approved leave for the assigned person)

- Team events (company meetings that reduce capacity)

- Saturday rules: The system supports complex Saturday schedules (all Saturdays working, none working, only 2nd and 4th off, etc.)

It only counts productive working hours per day:
 Daily Capacity = (Work End − Work Start − Lunch) × Productivity Factor

Example: 9 AM to 6 PM with 1-hour lunch, 80% productivity = (9 − 1) × 0.8 = 6.4 productive hours/day

### Delay Drift Calculation

Delay Drift = Predicted Completion Date − Deadline Date (in days)

- Positive drift = the task will finish AFTER the deadline (LATE)

- Zero drift = the task will finish ON TIME

- Negative drift = the task will finish BEFORE the deadline (EARLY)

### Risk Determination

| Condition | Risk Level |
| --- | --- |
| Drift > 2 days OR uncertainty > 35% of estimate | HIGH |
| Drift > 0 days OR uncertainty > 20% of estimate | MEDIUM |
| Everything else | LOW |

### Confidence Score Calculation

Raw Confidence = 100 − (Uncertainty × 3) − (Drift × 8) − (Overload × 20)

Clamped between 5% and 99%.

The system then calibrates this confidence using historical accuracy:

- It tracks how accurate past predictions were in each confidence bracket (50-60%, 60-70%, etc.)

- If the workspace has historically been overconfident in the 80-90% range (tasks predicted at 85% confidence actually missed deadlines frequently), it automatically reduces future 85% predictions by a penalty

- This self-correcting mechanism improves over time as more tasks are completed

### Additional Confidence Modifiers

- Senior-heavy teams get +3% confidence boost

- Junior-heavy teams get −5% confidence penalty

- Teams larger than 3 engineers get −3% (coordination overhead penalty)

- Context-aware adjustments: The system learns that certain task categories (e.g., "API integration") historically take longer and adjusts accordingly

### Example

Task: "Database Migration" — 24h estimated, 16h best, 24h likely, 40h worst
 Worker: Developer B, works 9AM-6PM, 60-min lunch, 80% productivity
 Calendar: 2 holidays this month, Developer B has 1 day leave

- Expected effort: (16 + 96 + 40) / 6 = 25.3 hours

- Uncertainty: (40 − 16) / 6 = 4 hours

- Daily capacity: 6.4 hours

- Adjusted effort: (25.3 + 0 + 4) × 1 / (1 × 1 × 1) = 29.3 hours

- Working days needed: 29.3 / 6.4 = 4.6 days

- Skipping holidays and leave: Completion predicted for next Thursday

- Deadline is next Wednesday → Drift = +1 day → Risk = MEDIUM, Confidence = ~72%

## SECTION 4: DEPENDENCY LOGIC

### What It Does

Dependencies declare that "Task B cannot start until Task A is finished." This creates a chain of execution order.

### Dependency Creation

When creating or editing a task, a user can select other tasks as dependencies. The system stores these as directed relationships: Task B depends on Task A.

### Circular Dependency Protection

Before any dependency is saved, the system runs a graph cycle detection algorithm. If adding "Task C depends on Task A" would create a loop (because Task A already depends on Task C through some chain), the system rejects the dependency and prevents it from being created. This stops deadlock situations where tasks are stuck waiting for each other forever.

### Dependency Blocking

The execution brain enforces dependency gates:

- A task cannot move to EXECUTING or DEPLOYING if it has active (unresolved) upstream dependencies

- A task cannot be marked as BLOCKED_DEPENDENCY if it has no active dependencies (prevents false blocking)

### Delay Propagation (The Cascade Effect)

This is one of the most critical pieces of business logic. When a task is delayed, the system automatically:

- Builds a "reverse graph" — mapping every task to all the tasks that depend on it

- Finds all downstream tasks affected by the delay

- For each downstream task, shifts its start date to begin after the delayed task's new completion date

- Recalculates new ETAs, risk levels, and confidence scores for every affected task

- Persists the new dates into the database

- Sends notifications if any downstream task shifts by 2+ days or reaches high risk

- Logs the entire cascade in the audit trail

### Example

Three tasks in a chain:

- Task A: "Design API" (deadline: June 1) → Task B depends on A

- Task B: "Build API" (deadline: June 10) → Task C depends on B

- Task C: "Test API" (deadline: June 15)

Task A gets delayed by 3 days (now finishes June 4 instead of June 1).

The cascade:

- Task B's start date shifts from June 2 to June 5 → new completion: June 13 (3-day delay)

- Task C's start date shifts from June 11 to June 14 → new completion: June 18 (3-day delay)

- Risk on Task C jumps from LOW to HIGH

- A notification fires: "Test API delayed +3d due to Design API change"

- All changes are logged in the immutable audit trail

## SECTION 5: BLOCKER LOGIC

### What It Does

Blockers are obstacles that prevent a task from progressing. They are distinct from dependencies — a dependency is a structural work-order relationship, while a blocker is an unexpected problem.

### Blocker Categories

- Client: Waiting for client input, approval, or feedback

- Data: Missing data, wrong data format, data access issues

- Infrastructure: Server down, build pipeline broken, environment unavailable

- Approval: Waiting for internal approval from a manager or stakeholder

- Dependency: Upstream work from another team hasn't been delivered

- Access: Missing credentials, security clearance, or system permissions

### Blocker Properties

- Description: What the problem is

- Owner: Who is responsible for resolving it

- Critical flag: Whether this blocker threatens the entire project timeline

- History: A log of all state changes (created → owner assigned → resolved)

### How Blockers Affect the System

Timeline Impact:

- When a blocker is created, the system records the start of a "wait period"

- When resolved, it records the end of the wait period

- The total wait time is subtracted from productive execution time

Friction Metrics:
 The system calculates organizational friction by analyzing all blockers:

- Infrastructure Instability %: What percentage of all blockers are infrastructure/access problems

- Coordination Latency %: What percentage are approval/client delays

- External Dependency Pressure %: What percentage are dependency/data issues

- Average Blocker Duration: How long, on average, blockers take to resolve

Risk Impact:

- Projects with unresolved critical blockers are automatically rated as "critical" risk

- Projects with any unresolved blocker are rated at least "high" risk

- Projects with historical blockers (even if resolved) are rated at least "medium" risk

Confidence Impact:

- Active blockers reduce confidence scores

- Each blocker deducts from the team's continuity score (explained in Section 7)

### Example

Task: "Integrate Payment Gateway"

- Developer starts work on Monday

- Tuesday: Blocker created — "Client hasn't provided sandbox API credentials" (Category: Client, Critical: Yes)

- The clock starts ticking on wait time

- Wednesday: PM escalates to client

- Thursday: Client provides credentials → Blocker resolved

- Wait time: 48 hours

- The task's predicted completion shifts forward by 2 working days

- The project's delivery confidence drops during the blocked period

## SECTION 6: EXECUTION STATE MODEL

### The Two-Layer State System

Resolve PM operates with two layers of state:

Layer 1: Board States (User-Visible)

| State | Meaning | Visual |
| --- | --- | --- |
| Backlog | Waiting to be prioritized | "Triage / Backlog" column |
| Ready | Cleared for work, waiting to start | "Ready" column |
| In Progress | Someone is actively working | "In Flight" column |
| Review | Work done, being validated | "Validation Roster" column |
| Done | Fully completed | "Done" column |

Layer 2: Execution Sub-States (Engine-Internal)

These provide granular tracking:

| Sub-State | Maps To Board State | Meaning |
| --- | --- | --- |
| EXECUTING | In Progress | Actively writing code / doing work |
| DEPLOYING | In Progress | Pushing to staging or production |
| TESTING | Review | Running QA / automated tests |
| VALIDATING | Review | Final acceptance testing |
| WAITING_FOR_CLIENT | Ready | Paused — client hasn't responded |
| WAITING_FOR_DATA | Ready | Paused — missing required data |
| WAITING_FOR_INFRASTRUCTURE | Ready | Paused — servers/tools unavailable |
| WAITING_FOR_APPROVAL | Ready | Paused — approval pending |
| BLOCKED_DEPENDENCY | Ready | Cannot proceed — upstream task incomplete |
| BLOCKED_INFRASTRUCTURE | Ready | Cannot proceed — environment broken |
| BLOCKED_ACCESS | Ready | Cannot proceed — missing permissions |
| CLIENT_VERIFICATION | Review | Client is reviewing/testing |
| RELEASE_WINDOW_PENDING | Ready | Ready to deploy but waiting for release window |
| INTERNAL_REVIEW | Review | Peer review in progress |

### State Transition Rules

- A task cannot move to EXECUTING if it has active upstream dependencies (the system blocks this)

- A task cannot be marked BLOCKED_DEPENDENCY if it has no active dependencies (prevents false flags)

- Any other transition is nominally allowed (the system trusts the PM's judgment)

### The Continuity Score

For each task, the system calculates a "continuity score" (0-100) that measures how smoothly work flowed:

- Starts at 100

- Loses 15 points per interruption (each time the task goes from active to waiting/blocked)

- Loses proportional points based on the ratio of wait time to total time

Example: A task that was active for 20 hours but waited for 10 hours with 2 interruptions:

- Wait ratio: 10/30 = 33%

- Score: 100 − (2 × 15) − (0.33 × 35) = 100 − 30 − 11.5 = 58.5

## SECTION 7: PROJECT HEALTH LOGIC

### Four Global Health Indicators

These are calculated server-side (in the database) across the entire workspace:

#### 1. Delivery Confidence (0-100%)

What it measures: How likely your workspace is to deliver everything on time.

How it's calculated:

- For every active project, the system aggregates all task-level PERT estimates

- It computes the "worst case scenario" using statistical spread (2 standard deviations above expected)

- The gap between expected and worst case is the "decay hours" (uncertainty)

- Delivery Confidence = 100 − (Total Decay Hours × 0.5)

Example: If your workspace has 30 hours of total uncertainty across all projects:
 Delivery Confidence = 100 − (30 × 0.5) = 85%

#### 2. Execution Pressure (0-100%)

What it measures: How overloaded and stressed the execution pipeline is.

How it's calculated:

- Counts blocked tasks vs. total active tasks across the workspace

- Adds the "spread pressure" from PERT variance across projects

- Pressure = (Blocked ÷ Active × 40) + Spread Pressure

Example: 5 blocked tasks out of 40 active = (5/40 × 40) + 10 = 15%

#### 3. Daily Fatigue

What it measures: The raw amount of uncertainty hours the team is carrying.

This is simply the total decay hours from the PERT calculation. It represents how many additional hours of work could materialize if things go wrong.

#### 4. Risk Forecast (0-100%)

What it measures: Overall risk of timeline failure.

How it's calculated:
 Risk = (Confidence Risk × 45%) + (Execution Pressure × 35%) + (Fatigue Risk × 20%)

Where Confidence Risk = 100 − Delivery Confidence, and Fatigue Risk = min(100, Fatigue × 2)

### Team-Level Health Indicators

#### Delivery Reliability Score (30-100)

- Starts at 85 baseline

- +1 for each completed task

- −2 for each incomplete task

- Clamped between 30 and 100

#### Continuity Stability Index (20-100)

- Starts at 100

- −12 for each active blocker affecting the team

- Measures how uninterrupted the team's work flow has been

#### Stream Pressure

- Total estimated hours of unfinished tasks divided by weekly capacity × 100

- Tells you if a work stream is overloaded (>100% = more work than capacity)

### Confidence Calibration (Self-Learning)

This is a unique feature. The system:

- Records every prediction it makes (e.g., "Task X at 82% confidence")

- When the task completes, measures the actual prediction error

- Groups predictions into buckets (50-60%, 60-70%, etc.)

- For each bucket, calculates historical accuracy rate

- Uses this history to adjust future predictions in the same bucket

If the 80-90% confidence bucket has historically been overconfident by an average of 4 days, future predictions in that bracket get a −12% penalty (4 days × 3).

## SECTION 8: ESCALATION LOGIC

### When the System Escalates

The system generates escalation recommendations (not automatic escalations) based on these conditions:

#### Time-Based Escalation

- Any blocker unresolved for more than 12 hours generates an escalation recommendation

- Non-critical blockers → escalate to PM

- Critical blockers → escalate to Super Admin

#### Risk-Based Escalation

- If a task's delay cascade shifts a downstream task by 2+ days or increases risk to HIGH → the system sends a notification classified as "risk"

#### Workload Overload

The system detects when one person has significantly more blocked tasks than others and recommends workload redistribution to available team members.

#### Dependency Failure Escalation

When a dependency type (e.g., "infrastructure") has a failure rate above 30% across all blockers, the system generates an organizational insight flagging it as systemically unstable.

#### Approval Bottleneck Detection

If any role's average approval latency exceeds 24 hours, the system flags an "Approval Bottleneck" and recommends a 12-hour auto-escalation policy.

### What Responses the System Recommends

For each active blocker, the Adaptive Response Engine generates:

- Execution Reroutes: "While Task X is blocked, start Task Y instead"

- Workload Redistribution: "Move this from Developer A to Developer B"

- Dependency Mitigations: "Use mock data interfaces to decouple from the delayed upstream task"

- Escalation Recommendations: "This has been stuck 18 hours — escalate to PM"

- Continuity Plans: "Project X has drifted 3+ days — propose shifting the deadline by 4 days and deferring low-priority tasks"

- Operational Fallbacks: For infrastructure blockers, specific steps like "Switch to local Docker containers" or "Use staging bypass keys"

## SECTION 9: NOTIFICATION LOGIC

### When Notifications Occur

| Trigger | Category | Recipient |
| --- | --- | --- |
| Timeline cascade shifts a task ≥2 days | Risk | Workspace-wide |
| Task risk changes to HIGH | Risk | Workspace-wide |
| Blocker created on a task | System | PM (via automation) |
| Sprint completed | System | Workspace-wide |
| Approval completed/rejected | System | Workspace-wide |
| Automation rule executed | System | Configured recipients |
| Leave approved | System | Affected team |

### Severity Levels

Notifications have categories, not explicit severity:

- Assignments: Task assigned to someone

- Deadlines: Deadline approaching or missed

- Risk: Timeline impact, risk level changes

- Attendance: Clock-in/out, leave events

- System: Automation events, sync completions

### Deduplication

The automation engine deduplicates triggers using a key composed of: event type + entity ID + timestamp. Events with identical keys within 1 second are suppressed. Additionally, the engine has a maximum recursion depth of 5 to prevent infinite loops where an automation triggers another automation that triggers the first one again.

### Delivery

Notifications are stored in the database and displayed in-app. The system also fires webhooks (external HTTP calls) for configured events, allowing integration with Slack, Teams, or custom systems. When the database is unavailable, notifications fall back to browser localStorage.

## SECTION 10: PROJECT COMPLETION LOGIC

### How "Project Completed" Is Determined

Currently, there are NO automated completion conditions.

A project is completed when a PM or Super Admin manually changes its status to "done" or "deployed." The system does not enforce:

- ❌ All tasks must be "done"

- ❌ All blockers must be resolved

- ❌ All dependencies must be satisfied

- ❌ Approval chains must be completed

- ❌ Client sign-off must be recorded

This is entirely discretionary. A PM could mark a project "done" with 3 open tasks, 2 active blockers, and unresolved dependencies. The system would allow it.

### What Does Happen on Completion

- The project status changes in the database

- An activity log entry is written to the immutable audit trail

- The project stops appearing in active dashboards

- The project's tasks stop contributing to workspace-level health metrics (delivery confidence, execution pressure)

- Any active impact simulations related to this project become stale

### Impact Simulations on Completion

Impact simulations have a built-in staleness mechanism:

- Each simulation has an expiration time (default: 24 hours)

- If the underlying task data changes (detected via fingerprinting), the simulation is marked stale

- Stale simulations cannot be applied — new ones must be generated

## SECTION 11: ROLE BEHAVIOR MODEL

### Super Admin

What they see: Everything. Full visibility into all projects, tasks, teams, analytics, governance, audit logs, system health, mission control, integrations, automations, and security controls.

What they can do: Everything. Create/edit/delete projects, tasks, teams. Reassign tasks. Modify priorities, risk, confidence. Manage integrations, automations, approval chains. Access platform governance (role management, security policies). Manage settings. View the audit trail. Override any developer restriction.

What they cannot do: Nothing is restricted.

### PM (Project Manager)

What they see: Projects, tasks, scheduling, analytics, decision center, reports, logistics, teams, stakeholders, settings, integrations, automations.

What they can do: Create/manage projects and tasks. Assign/reassign work. Set priorities and risk levels. Configure integrations and automations. Manage team membership. Access analytics and reports. Change settings.

What they cannot do: Cannot access platform governance (role management beyond their workspace). Cannot access the Mission Control intelligence panel. Cannot access security-level controls.

### Developer

What they see: Projects (view only), tasks (with restrictions), scheduling (view only), teams (view only).

What they can do: Change task status (move tasks across board columns). Update task descriptions and estimated hours. Add comments.

What they cannot do:

- Cannot create projects or tasks

- Cannot reassign tasks (database enforced)

- Cannot move tasks between projects (database enforced)

- Cannot change priority (database enforced)

- Cannot modify risk, confidence, predicted completion, or delay drift (database enforced)

- Cannot access analytics, decision center, reports, logistics, settings, integrations, automations, governance, or security

### Viewer

What they see: Projects, tasks, scheduling, analytics, decision center, reports, teams, stakeholders, audit logs. Read-only access to nearly everything.

What they can do: View. Nothing else. Cannot create, edit, delete, or modify anything.

What they cannot do: Any write operation.

### Rate Limiting

All users are subject to a frontend mutation rate limit: no more than 30 data-modifying operations per 10-second window. Exceeding this triggers an error message and blocks further operations temporarily.

## SECTION 12: REAL-WORLD SCENARIO WALKTHROUGH

### Scenario: "Deploy Client ERP System"

Setup:

- Company: Acme Software Solutions

- Workspace configured: India, Mon-Sat (2nd & 4th Saturday off), 9:30 AM to 6:30 PM, 1-hour lunch, 80% productivity factor

- Team: PM Sarah, Developers Arjun, Priya, and Ravi

Day 1: Project Creation

Sarah creates the project:

- Name: "Deploy Client ERP System"

- Template: Enterprise Delivery (SDLC mode)

- Priority: Urgent

- Client Deadline: June 30

- Team: Assigned to the Engineering Team

Resolve PM: Project created in "planning" status. An audit log entry is written: "project_created." Delivery confidence is unaffected (no tasks yet).

Day 2: Task Creation

Sarah creates 6 tasks:

| Task | Hours | Dependencies | Assigned |
| --- | --- | --- | --- |
| Requirements Gathering | 16h | None | Sarah |
| Database Schema Design | 24h | Requirements | Arjun |
| API Development | 40h | Database Schema | Priya |
| Frontend Integration | 32h | API Development | Ravi |
| QA Testing | 24h | Frontend | Arjun |
| Client UAT | 16h | QA Testing | Sarah |

Resolve PM: Each task gets a PERT analysis. With the given hours as "likely" estimates, the system predicts:

- Total estimated: 152 hours

- Daily capacity per person: (9 hours − 1 hour) × 0.8 = 6.4 hours

- Predicted completion date: ~June 24 (with calendar adjustments)

- Delivery Confidence: ~87% (moderate uncertainty, comfortable buffer)

- Delay Drift: −6 days (ahead of deadline) → Risk: LOW

Day 8: Blocker Occurs

Arjun is working on "Database Schema Design" when the client's existing ERP database server goes down. He can't extract the current schema.

Arjun logs a blocker:

- Category: Infrastructure

- Description: "Client's ERP database server is unreachable — cannot extract current schema for migration mapping"

- Critical: Yes

Resolve PM:

- The blocker engine records the start of a wait period

- Arjun's task continuity score begins degrading

- The adaptive response engine generates:

  - Reroute: "While Database Schema is blocked, Ravi could start Frontend wireframes"

  - Operational Fallback: Steps to set up a local mock database

  - Escalation: "Blocker is critical — recommend escalating to Super Admin"

- Infrastructure instability metric increases

- Delivery confidence drops from 87% to ~75%

Day 10: Client Delay

The client's server is still down. The blocker has been active for 48 hours.

Resolve PM:

- Escalation recommendation fires: "Blocker has remained unresolved for 48 hours. Requires administrative override."

- The adaptive response engine now also generates a Continuity Plan: "Propose shifting the client deadline by 4 days and deferring Client UAT"

- The intelligence engine detects an "Infrastructure Node Volatility" pattern

Day 12: Dependency Impact

Client server comes back. Arjun resolves the blocker.

Resolve PM:

- Blocker resolution recorded. Total wait: 96 hours (4 working days)

- Database Schema Design predicted completion shifts from Day 10 to Day 14

- Dependency cascade fires:

  - API Development shifts from Day 15 start to Day 19 start → new completion: Day 25

  - Frontend Integration shifts accordingly → new completion: Day 29

  - QA Testing → Day 32

  - Client UAT → Day 35

- New predicted project completion: July 5 (5 days past deadline)

- Delay Drift: +5 days → Risk: HIGH

- Delivery Confidence: 52%

- Notifications fire for all affected tasks: "API Development delayed +4d due to Database Schema change"

- Impact simulation is generated and offered to Sarah with mitigation options:

  - "Split API Development into parallel subtasks" (saves 3 days)

  - "Move milestone by +5d to reflect actual timeline"

  - "Reassign high-risk tasks to available senior developer"

  - "Increase team capacity — add one developer"

  - "Reduce sprint scope — move Client UAT to next phase"

  - "Compress timeline — increase productivity factor to 0.95 for 2 weeks"

Day 13: Escalation and Resolution

Sarah accepts the "Split API Development" mitigation. She breaks the 40-hour API task into two parallel 20-hour subtasks.

Resolve PM:

- New ETA recalculated with parallel execution

- Predicted completion shifts to July 2 (2 days past deadline)

- Delivery Confidence recovers to 65%

- The learning engine records that the "split task" mitigation was successful

- The confidence calibration service records the prediction accuracy for future adjustment

Day 28: Completion

All tasks reach "done." Sarah moves the project status to "deployed."

Resolve PM:

- Final audit log entries recorded

- The confidence calibration service compares predicted vs. actual completion for each task

- The learning engine updates:

  - Infrastructure trust score decreases (the 4-day outage is remembered)

  - Team recovery performance profile is updated (96-hour blocker resolved, mitigation adopted)

  - Delivery behavior profile for this project: 5-day historical drift, 83% sprint completion ratio

- These learnings will influence future predictions for similar projects

## FINAL SECTION: HONEST ASSESSMENT

### 1. Logic That Is Excellent

- PERT-based estimation with calendar-aware scheduling. This is genuinely sophisticated. The system doesn't just say "40 hours = 5 days." It accounts for holidays, leaves, Saturday rules, team events, productivity factors, and even partial availability. This is production-grade scheduling logic that most PM tools lack.

- Dependency cascade propagation. Automatically detecting downstream impacts, recalculating ETAs, shifting start dates, and notifying affected parties — this is exactly what a real operations team needs. The reverse-graph traversal and persistent propagation is well-implemented.

- Confidence calibration self-learning. The system tracking its own prediction accuracy and self-correcting over time is genuinely innovative. This means predictions get more accurate the longer the workspace is used.

- Immutable audit trail with hash chains. The blockchain-style audit log with WORM (Write Once, Read Many) database rules means audit records literally cannot be tampered with, even by database administrators. This is enterprise-grade compliance infrastructure.

- Database-enforced role restrictions. Developer restrictions aren't just frontend UI hiding — they're PostgreSQL trigger-level enforcement. A developer cannot reassign a task even if they directly access the API. This is the correct way to implement authorization.

- Circular dependency detection. The DFS cycle detection prevents deadlock situations where tasks would be stuck waiting for each other forever.

### 2. Logic That Is Confusing

- Two overlapping state systems. The board has 5 states (backlog, ready, in_progress, review, done) and the execution engine has 14 sub-states (EXECUTING, DEPLOYING, WAITING_FOR_CLIENT, etc.). But the mapping between them is lossy — WAITING_FOR_CLIENT, BLOCKED_DEPENDENCY, and WAITING_FOR_APPROVAL all map to "ready." A PM looking at the board sees a task in "Ready" but doesn't know if it's actually blocked, waiting for a client, or genuinely ready to work on. This is a significant UX gap.

- "Planning" vs "Active" vs "In-Progress" project statuses. There are 7 project states, and the distinction between "active" and "in-progress" is unclear. When does a project transition from "active" to "in-progress"? The system provides no guidance or enforcement.

- Task "deadline" vs "due_date" vs "client_deadline". There are three date fields that represent similar concepts. The codebase itself marks due_date as deprecated and says it mirrors deadline, but both exist in the database. This will confuse anyone reading the data.

### 3. Logic That May Not Reflect Real Business Operations

- Team delivery reliability score starts at 85 and adjusts by +1 per completed task and −2 per incomplete task. In reality, a team with 100 completed tasks and 5 incomplete ones would have a score of 85 + 100 − 10 = 175, clamped to 100. This means the score is nearly always at 100 for any team that has finished more than 8 tasks, regardless of how badly they're performing on current work. It measures cumulative completion, not current reliability.

- Blocker frequency per sprint divides by a hardcoded "2 sprints" baseline assumption. This is arbitrary and doesn't reflect actual sprint count. A project that has run 10 sprints will appear to have artificially high blocker frequency.

- The "risk trend" chart in the intelligence engine uses a synthetic 7-day simulation with mathematical smoothing, not actual historical data. The risk scores shown on the trend chart are fabricated approximations, not real measurements. Business stakeholders should be aware that this is a projection, not a recording.

- Infrastructure reliability categories are hardcoded to "AWS Cluster", "Database Server", "CI/CD Pipeline", and "Security Gateway." These are arbitrary labels that may not match a company's actual infrastructure. Blocker descriptions are keyword-matched against these labels.

### 4. Logic That Could Cause Wrong Project Predictions

- Attendance and availability factors default to 1.0. Unless someone actively maintains attendance records and availability data, the system assumes everyone is always at work and always available. This makes predictions optimistic by default. A company that doesn't track attendance will get systematically overconfident predictions.

- Team load factor defaults to 1.0 (no overload). But if a developer is assigned tasks across 3 projects simultaneously, the system doesn't automatically detect this and increase the load factor. It only applies if explicitly set. Multi-project workloads are invisible by default.

- No automatic detection of over-assignment. If Developer A has 200 hours of active work across multiple projects, but each project's ETA calculation assumes Developer A is 100% available for that project, all predictions will be wrong. The system doesn't account for a person's total workload across projects when predicting individual task completion.

- The Operational Replay (historical snapshot simulation) uses synthetic calculated snapshots, not actual recorded snapshots. The "blocked task count 3 days ago" is approximated by subtracting from current counts, not by querying what the actual count was 3 days ago.

### 5. Logic That Should Be Changed Before Locking

- Project completion should have optional enforcement gates. At minimum, offer a configurable option: "Warn if marking project done with unfinished tasks" or "Block project completion until all tasks are done." Currently, there is zero safety net.

- The 14-state execution sub-state system is unused by the actual board. The sub-states (WAITING_FOR_CLIENT, BLOCKED_INFRASTRUCTURE, etc.) are defined and the engine can process them, but the user-facing board only shows 5 columns. Either surface these sub-states in the UI (as task badges, filters, or sub-columns) or remove them. Currently they create code complexity with no user-visible benefit.

- Team delivery reliability scoring formula needs rethinking. The +1/−2 per-task formula is simplistic and quickly saturates. Consider using a rolling-window metric (e.g., "percentage of tasks completed on time in the last 30 days") instead of cumulative all-time counts.

- Multi-project workload should be automatically detected. When a person is assigned tasks across multiple projects, the system should automatically calculate their actual available capacity per project and adjust ETAs accordingly. This is the single biggest source of prediction error.

- Notification workspace_id is sometimes empty string. The approval service passes workspace_id: '' in several activity log entries and webhook calls. This would cause audit trail entries to be disconnected from their workspace.

### 6. Logic That Is Safe To Permanently Lock

- The PERT calculation formula — (Best + 4 × Likely + Worst) / 6. This is an industry-standard formula with decades of validation. Lock it.

- The calendar-aware scheduling engine — the work window, holiday, leave, and Saturday rule logic. This is thorough, handles edge cases (partial availability, team events with capacity reduction), and has a safety loop limit (2000 iterations). Lock it.

- The circular dependency detection algorithm. Standard DFS cycle detection on a directed graph. Mathematically proven correct. Lock it.

- The immutable audit trail with WORM rules. The database rules preventing UPDATE and DELETE on audit records, combined with hash chains, are production-grade compliance infrastructure. Lock it.

- The database-level developer restriction triggers. These prevent privilege escalation at the most secure layer possible. Lock them.

- The rate limiting mechanism (30 mutations per 10 seconds). Simple, effective, prevents abuse. Lock it.

- The confidence calibration self-learning loop. The bucket-based historical accuracy tracking and penalty adjustment is mathematically sound and self-improving. Lock it.

- The dependency cascade propagation. The graph traversal, downstream detection, ETA recalculation, and notification pipeline is correct and comprehensive. Lock it.

This concludes the Resolve PM Execution Engine Extraction & Business Logic Documentation Audit.